## Sheet1
DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN FOR 2023/2024 FINANCIAL YEAR: PLANNING & DEVELOPMENT
IDP Reference | Project Number | National KPA / B2B Pillars | Objectives | Strategy | Key Performance Indicator | Unit of Measure | Baseline | Budget | Annual Target | QUARTER 1 |  |  | QUARTER 2 |  |  | QUARTER 3 |  |  | QUARTER 4 |  |  | Progress Report towards achievement of targets | Blockages / Challenges | Corrective Measures taken / to be taken and date of finalisation | Wards | POE Required
[10 empty] | 1 July 2023 - 30 September 2023 |  |  | 1 October 2023 - 31 December 2023 |  |  | 1 January 2024 - 31 March 2024 |  |  | 1 April 2024 - 30 June 2024
[10 empty] | Performance Target | Actual Performance Target | Actual Budget Spent | Performance Target | Actual Performance Target | Actual Budget Spent | Performance Target | Actual Performance Target | Actual Budget Spent | Performance Target | Actual Performance Target | Actual Budget Spent
KZN266-DPL-SO 9 | DPL 1 | KPA: BASIC SERVICE DELIVERY/B2B PILLAR 2: BASIC SERVICE DELIVERY | To address the demand of housing within the Ulundi Municipal Area | Identification and prioritisation of housing projects within the municipal area | Prepare and Adopt Human Settlement Plan | Number | n/a | R315 000.00 | Prepare and Adopt the Human Settlement Plan by 30 June 2024 | Prepare Inception report by 30 September 2023 |  |  | Preparation of the Draft Human Settlement Plan 31 December 2023 |  |  | n/a |  |  | Adoption of Final Human Settlement Plan by Council by 30 June 2024 | [5 empty] | All 24 Wards | Inception Report; Draft Human Settlement Plan; Final Human Settlement Plan & Council Resolution
KZN266-DPL-SO 10 | DPL 2 |  | To ensure availability of Council Owned land for residential, commercial and industrial development | Promotion of a spirit of co-operation with traditional leadership to facilitate access to Council Owned land within the traditional authority areas | Redrafting of the proclamation diagram | Date | 0 | R661 500.00 | Redrafting of the proclamation diagram by 30 June 2024 | Prepare Inception report by 30 September 2023 |  |  | n/a |  |  | Draft Report by 31 March 2024 |  |  | Final Report by 30 June 2024 | [5 empty] | All 24 Wards | Inception Reports ;Darft Reports; Final Reports
KZN266-DPL-SO 13 | DPL 3 |  | To address the demand of housing within the Ulundi Municipal Area | Management of the construction and completion of all funded housing projects | Number of Quarterly Housing Forum Meetings convened | Number | 0 | n/a | 4 Quarterly Housing Forum Meetings convened by 30 June 2024 | 1 Quarterly Housing Forum convened by 30 September 2023 |  | n/a | 1 Quarterly Housing Forum convened by 31 December 2023 |  | n/a | 1 Quarterly Housing Forum convened by 31 March 2024 |  |  | 1 Quarterly Housing Forum convened by 30 June 2024 | [5 empty] | All 24 Wards | Agenda, Minutes & Attendance Registers
KZN266-DPL-SO 36 | DPL 4 | KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION / B2B PILLAR 3: GOOD GOVERNANCE | To promote good governance, accountability and transparency | Promotion of effective communication with internal and external stakeholders | Number of Quarterly Cogta Circular 88 Templates submitted by Department to the office of the Municipal Manager | Number | 4 | n/a | 4 Quarterly Cogta Circular 88 Templates submitted by Department to the office of the Municipal Manager by 30 June 2024 | 1 Quarterly Cogta Circular 88 Template submitted by Department to the office of the Municipal Manager by 30 September 2023 |  | n/a | 1 Quarterly Cogta Circular 88 Template submitted by Department to the office of the Municipal Manager by 31 December 2023 |  | n/a | 1 Quarterly Cogta Circular 88 Template submitted by Department to the office of the Municipal Manager by 31 March 2024 |  |  | 1 Quarterly Cogta Circular 88 Template submitted to the office of the Municipal Manager by 30 June 2024 | [5 empty] | All 24 Wards | COGTA Circular 88 Template & Proof of date of submission to the office of the Municipal Manager
KZN266-CS-SO 45 | DPL 5 |  | To promote good governance, accountability and transparency | Management of risk within the structures and operations of the Municipality | Number of Monthly Risk Register Progress Reports submitted by the 14th of each month by Head of Department to Risk Management Unit | Number | 12 | n/a | 12 Monthly Risk Register Progress Reports submitted by the 14th of each month by Head of Department by 30 June 2024 | 3 Monthly Risk Register Progress Report submitted by the 14th of each month by HOD by 30 September 2023 |  | n/a | 3 Monthly Risk Register Progress Report submitted by the 14th of each month by HOD by 31 December 2023 |  | n/a | 3 Monthly Risk Register Progress Report submitted by the 14th of each month by HOD by 31 March 2024 |  |  | 3 Monthly Risk Register Progress Report submitted by the 14th of each month by HOD by 30 June 2024 | [5 empty] | All 24 Wards | Quarterly Risk Register Progress Reports submitted & Proof of date of submission to Risk Management Unit
KZN266-CS-SO 45.1 | DPL 5.1 |  | To promote good governance, accountability and transparency | Management of risk within the structures and operations of the Municipality | Number of Quarterly Assessments of the Performance of Service Provider/s submitted by Head of Department to the Municipal Manager after the end of each quarter | Number | 4 | n/a | 4 Quarterly Assessments of the Performance of Service Provider/s submitted by Head of Department to the Municipal Manager by 30 June 2024 | 1 Quarterly Assessment of the Performance of Service Provider/s submitted by HOD to the MM for Q1 ending (30 September 2023) |  | n/a | 1 Quarterly Assessment of the Performance of Service Provider/s submitted by HOD to the MM for Q2 ending (31 December 2023) |  | n/a | 1 Quarterly Assessment of the Performance of Service Provider/s submitted by HOD to the MM for Q3 ending (31 March 2024) |  |  | 1 Quarterly Assessment of the Performance of Service Provider/s submitted by HOD to the MM for Q4 ending (30 June 2024) | [5 empty] | All 24 Wards | Assessment of the Performance of Service provider signed by the HOD and Proof of submission to the Municipal Manager
KZN266-DPL-SO 51 | DPL 6 |  | Promotion of integrated and coordinated development within the Municipality | Annual Review of the Integrated Development Plan | Date of Preparation and approval of the IDP Document by Council | Date | n/a | R606 375.00 | Preparation and approval of the IDP Document by Council by 30 June 2024 | Preparation and adoption by Council of the IDP process plan and advertisement by 30 September 2023 |  | n/a | Appointment of Service Provider for preparing IDP by 31 December 2023 |  |  | Council approval of Draft IDP Document by 31 March 2024 |  |  | Adoption of the Final IDP Document by Council by 30 June 2024 | [5 empty] | All 24 Wards | Process Plan & Council Resolution, Advert, and Council Resolution adopting the Final IDP Document
KZN266-DPL-SO 51.1 | DPL 6.1 |  | Promotion of integrated and coordinated development within the Municipality | Annual Review of the Integrated Development Plan | Number of IDP Roadshows /Public Consultation held | Number | n/a | R551 250.00 | 1 IDP Roadshow/Public Consultation held by 30 June 2024 | n/a |  |  | n/a | n/a |  | n/a |  |  | 1 IDP Roadshow held by 30 June 2024 | [5 empty] | All 24 Wards | Public Notice, Attendance Registers and photos
KZN266-DPL-SO 51.2 | DPL 6.2 |  | Promotion of integrated and coordinated development within the Municipality | Annual Review of the Integrated Development Plan | % of IDP Credibility Score obtained from COGTA IDP Assessment | Percentage | n/a | n/a | 50% or more IDP Credibility Score achieved for the IDP Assessment by COGTA by 30 June 2024 | n/a |  |  | 50% or more IDP Credibility Score achieved for the IDP Assessment by COGTA by 31 December 2023 |  | n/a | n/a |  |  | n/a | [5 empty] | All 24 Wards | MEC IDP Assessment letter with Credibility Score
KZN266-DPL-SO 52 | DPL 7 |  | Promotion of integrated and coordinated development within the Municipality | All development within the Municipality is guided by the IDP | Number of IDP Forums / Stakeholder Engagements held | Number | n/a | R150 000.00 | 1 IDP Forum /Stakeholder Engagements held by 30 June 2024 | n/a |  |  | n/a |  |  | n/a |  |  | 1 IDP Forum /Stakeholder Engagement held by 30 June 2024 | [5 empty] | All 24 Wards | Attendance Registers and Minutes of the IDP Forum/Stakeholders
KZN266-DPL-SO 55 | DPL 8 | KPA: MUNICIPAL FINANCIAL VIABILITY & MANAGEMENT / B2B PILLAR 4: SOUND FINANCIAL MANAGEMENT | To ensure that the municipality remains financially viable | To effectively and efficiently manage the municipality's cash flow | Collection of budgeted Revenue for the Directorate for 2022/2023 financial year amounting to R150 000.00 | Rand Value | 0 | R143 805.00 | Collection of budgeted Revenue for the Directorate for 2022/2023 financial year amounting to R143 805.00by 30 June 2024 | Collection of budgeted Revenue for the Directorate for 2022/2023 financial year amounting to R35 951.25 by 30 September 2023 |  | n/a | Collection of budgeted Revenue for the Directorate for 2022/2023 financial year amounting to R143 805.00 by 31 December 2023 |  | n/a | Collection of budgeted Revenue for the Directorate for 2022/2023 financial year amounting to R143 805.00 by 31 March 2024 |  |  | Collection of budgeted Revenue for the Directorate for 2022/2023 financial year amounting to R143 805.00 by 30 June 2024 | [5 empty] | All 24 Wards | Income and expenditure report
KZN266-DPL-SO 55.1 | DPL 8.1 |  | To ensure that the municipality remains financially viable | To effectively and efficiently manage the municipality's cash flow | Containment of operational expenditure budget for the Directorate for 2022/2023 financial year within budgetary limits of R4 147 612.90 | Rand Value | 0 | R6 685 645.00 | Containment of operational expenditure budget for the Directorate for 2022/2023 financial year within budgetary limits of R6 685 645.00 by 30 June 2024 | Containment of operational expenditure budget for the Directorate for 2022/2023 financial year within budgetary limits of R1 671 411.25 by 30 September 2023 |  | n/a | Containment of operational expenditure budget for the Directorate for 2022/2023 financial year within budgetary limits of R1 671 411.25 by 31 December 2023 |  |  | Containment of operational expenditure budget for the Directorate for 2022/2023 financial year within budgetary limits of R1 671 411.25 by 31 March 2024 |  |  | Containment of operational expenditure budget for the Directorate for 2022/2023 financial year within budgetary limits of R1 671 411.25 by 30 June 2024 | [5 empty] | All 24 Wards | Income and expenditure report
KZN266-DPL-SO 58 | DPL 9 |  | Ensure the maintenance of sound financial practices | To work towards obtaining a Clean Audit Report from the Auditor-General | Number of Monthly Progress Reports on AG Action Plan submitted to the Municipal Manager | Number | 12 | n/a | 12 Monthly Progress Reports on the implementation of A-G Action Plan submitted to the Municipal Manager by 30 June 2024 | 3 Monthly Progress Reports on the implementation of A-G Action Plan submitted to the Municipal Manager by 30 September 2023 | n/a | n/a | 3 Monthly Progress Reports on the implementation of A-G Action Plan submitted to the Municipal Manager by 31 December 2023 | n/a | n/a | 3 Monthly Progress Reports on the implantation of A-G Action Plan submitted to the Municipal Manager by 31 March 2024 |  |  | 3 Monthly Progress Reports on the implementation of A-G Action Plan submitted to the Municipal Manager by 30 June 2024 | [5 empty] | All 24 Wards | Progress Reports and Proof of submission
KZN266-DPL-SO 60 | DPL 10 | KPA: SPATIAL AND ENVIRONMENTAL | Promotion of integrated and coordinated spatial development within the municipality | Approve and Implement the reviewed SDF | Preparation and adoption of the Spatial Development Framework | Date | n/a | R525 000.00 | Preparation and adoption of the Spatial Development Framework by 30 June 2024 | Prepare an Inception Report by 30 September 2023 |  |  | Prepare Draft SDF by 31 December 2023 | Nil | Nil | Advertisement of Draft SDF by 31 March 2024 |  |  | Adoption of the Final SDF by Council by 30 June 2024
KZN266-DPL-SO 61 | DPL 11 |  | Promotion of integrated and coordinated spatial development within the municipality | Ensure creation of an enabling environment through improvement of Spatial and Land Use Development | Registration ( Convencing) of properties at Ulundi CBD | Date | n/a | R663 390.00 | Registration ( Conveyancing) of properties at Ulundi CBD by 30 June 2024 | Prepare Project Work- Plan by 30 September 2023 |  |  | Progress Report on the registration of properties at Ulundi CBD (Ulundi BA) by 31 December 2023 | Nil | Nil | Progress Report on the registration of properties at Ulundi CBD (Ulundi BA) by 31 March 2024 |  |  | Progress Report on the registration of properties at Ulundi CBD (Ulundi BA) by 30 June 2024
KZN266-DPL-SO 61.1 | DPL 11.1 |  | Promotion of integrated and coordinated spatial development within the municipality | Ensure creation of an enabling environment through improvement of Spatial and Land Use Development | Unit A Layout Amendment | Date | n/a | R347 288.00 | Registration ( Conveyancing) of properties at Ulundi Unit A by 30 June 2024 | Prepare Project Work- Plan by 30 September 2023 |  |  | Progress Report on the registration of properties at Ulundi Unit A by 31 December 2023 |  |  | Progress Report on the registration of properties at Ulundi Unit A by 31 March 2024 |  |  | Progress Report on the registration of properties at Ulundi Unit A by 30 June 2024 | [5 empty] | 18 | Project workplan, Progress Reports
KZN266-DPL-SO 63 | DPL 12 |  | To ensure that the Municipality’s development strategies and projects take cognizance of environmentally sensitive areas and promote the protection of environmental assets | Ensure that due consideration is given to the impact on the environment caused by the programmes and projects planned and implemented within the municipal area | Number of Monthly inspections done within 4 days of receiving inspection form (buildings under construction) | Number | 0 | n/a | 12 Monthly inspections done within 4 days of receiving inspection form (buildings under construction) by 30 June 2024 | 3 Monthly inspections done within 4 days of receiving inspection form (buildings under construction) by 30 September 2023 |  | n/a | 3 Monthly inspections done within 4 days of receiving inspection form (buildings under construction) by 31 December 2023 |  |  | 3 Monthly inspections done within 4 days of receiving inspection form (buildings under construction) by 31 March 2024 |  |  | 3 Monthly inspections done within 4 days of receiving inspection form (buildings under construction) by 30 June 2024 | [5 empty] | All 24 Wards | Inspection Forms
KZN266-DPL-SO 63.1 | DPL 12.1 |  | To ensure that the Municipality’s development strategies and projects take cognizance of environmentally sensitive areas and promote the protection of environmental assets | Ensure that due consideration is given to the impact on the environment caused by the programmes and projects planned and implemented within the municipal area | % of Building Plans approved within 30 days of meeting all requirements | Percentage | n/a | n/a | 100 % of Building Plans approved within 60 days of meeting all requirements by 30 June 2024 | 100 % of Building Plans approved within 60 days after meeting all the requirements by 30 September 2023 |  | n/a | 100 % of Building Plans approved within 60 days of meeting all requirements by 31 December 2023 |  |  | 100 % of Building Plans approved within 60 days of meeting all requirements by 31 March 2024 |  |  | 100 % of Building Plans approved within 60 days of meeting all requirements by 30 June 2024 | [5 empty] | All 24 Wards | Building Plan Register, Letter of Approval / Disapproval Letter